Select any team name you prefer.
Please enter your name as it appears in Blackboard.
This is the priority ranking for this feature, relative to all other features.

Lower integers are higher in prioirty.

The customer may add or (for unimplemented features) remove features and change priority rankings at the start of each sprint.
This is the sprint during which the grader will grade your implementation of this feature.

By the END of this sprint, you must have implemented this feature.

If this field is blank, then this is a bonus feature. If implemented, it will be graded after the final sprint for extra credit.
This is the MAXIMUM number of bonus points awarded if you successfully and completely implement this feature.

If blank, this feature is REQUIRED. You MAY NOT work on ANY bonus feature until ALL required features have been implemented.

If non-blank, some or all bonus points will be awarded ONLY if the feature is COMPLETELY implemented.
 Complete but non-optimal implementations may receive partial credit.
Incomplete or nearly-complete implementations will receive no bonus points.
This is the professor's estimate as to the relative difficulty of this feature in "points".

Points are unitless, and only have meaning relative to other estimates (a 2 point feature is expected to take about twice as long as a 1 point feature).

In a real project, points are assigned via a game of "estimating poker" played by the entire team.
Select the sprint number (1, 2, etc.) in which you plan to implement this feature. This is just for planning purposes, it won't affect your grade.

In Scrum, you only plan the current sprint, not future sprints, so you don't need to fill this in for any features not planned for the current sprint.

If you planned a "full credit" feature for the current sprint but don't complete it, then just update this cell for the next sprint. This will only affect your grade if this feature was *required* to be completed by a specific sprint, and is not.

If you planned a "bonus" or "extreme bonus" feature for the current sprint but don't complete it, and you don't want to use it for the next sprint, just use the Delete key to leave this cell blank. Your "full credit" grade will not be penalized for this decision.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
Leave blank initially (hint: Use the Delete key)
Select "In Work" when you begin designing and coding this feature.
Select "In Test" when this feature is fully coded and you are testing it.
Select Finished ONLY when the feature works well and is READY TO SHIP.
    "Finished in Sprint 1" means it was delivered at the end of Sprint 1.
    "Finished in Sprint 2" - "Finished in Sprint 6" are the same for those sprints.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
Please enter 2 or 3 capital letters that will represent you in the "Assigned To" column on each Sprint Backlog tab of this spreadsheet.
Please enter your UTA student ID number.
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
The list contains the Feature IDs from the same column on the Product Backlog tab.

For each (ahem) Feature ID, create one or more rows in this table representing the tasks you need to complete to implement that feature.

For example, for a "Provide Help to User" feature, you might assign a Feature ID of "HELP" on the Product Backlog. Then, in the Sprint Backlog table, you might have 3 rows of tasks with Feature ID of Help - "Write help text", "Create help class to display help", and "Update CLI to accept '?' command".

COPY the status cell from row 1 for each row that you add, so that you can select its status with a drop-down. This will ensure that the Sprint Burn Chart at the top updates itself automatically as you complete your tasks.
Exactly ONE team member may be responsible for any task, and they will receive grade credit for their work.

If you have more than one person on your team, each member MUST select their initials for each task the agree to perform. Use this to ensure that no duplicate work occurs, and that no tasks "fall through the cracks".

If you are wroking individually, you do NOT need to put your initials next to every task. We'll figure out who did the work. Somehow.
Select a Feature ID to the left. Then, in this column, list each discrete task needed to implement that feature.

Example tasks might be "create the Foo class", "add the Bar method to the (existing) Qux class", "Find icons for the task bar", "Update the manual to cover this feature", or "Fix the seg fault bug".

Expect roughly 3 to 10 tasks per typical feature. Don't OVER plan, but also don't just write "Implement the feature". Find a middle ground. :-)
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
## Product Backlog
Product Name:	Mav’s Animal Shelter Software (MASS)					Complete Fields in Green!!!
Team ID:

	Team Member Name					Initials	Student ID
Required

Sprint #	Remaining	Completed This Sprint				Comment
0	24				Total	Total number of features (in column H)
1	24	0			1	Total features left at the end of Sprint #1
2	24	0			2	Total features left at the end of Sprint #2
3	24	0			3	...and so on
4	24	0
5	24	0

				Note: Priority and specs for unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
				Additional features may be proposed by the student but must be approved by the Product Owner in writing
				Sprints
Feature ID	Priority	Required	Bonus	Est	Planned	Status	As a...	I want to...	So that I can…	Notes
EXIT	1	1		5			User	Exit the GUI program (File > Exit)	Use it again another day	Baseline an existing project’s code for class Mainwin, main function, and Makefile from e.g., MUSS (P6 – recommended), Nim (13), or Paint (17). Pare down GUI to what’s definitely reusable. Requires Mainwin::on_quit_click.
DOG	2	1		21			Staff	Create a new dog (Animal > New)	Track dogs seeking good homes	Requires Mainwin::on_create_animal; 1 dialog; classes Animal and Dog; Shelter::add_animal and attributes; and enum classes Gender and Dog_breed
LANIM	3	1		5			Staff	List animals (Animal > List Available)	See what animals are available	Requires Shelter::num_animals and animal; and Mainwin::on_animals_list; probably operator<< for dog
CAT	4	2		8			Staff	Create and list cats as well	Also put cats up for adoption	Requires class Cat; 1 Mainwin dialog to select Dog or Cat for Animal > New; and enum class Cat_breed; probably operator<< for Cat
RABBIT	5	2		8			Staff	Create and list rabbits as well	Also put rabbits up for adoption	Requires class Rabbit; and enum class Rabbit_breed; probably operator<< for Rabbit
CLIENT	6	2		13			Staff	Create a new client (Client > New)	Track candidate adopters	Requires Mainwin::on_create_client; 1 dialog; class Client; Shelter::add_client and attributes
LCLIENT	7	3		5			Client	List clients (Client > List)	See which clients are available	Requires Shelter::num_clients and client; and Mainwin::on_clients_list
ADOPT	8	3		5			Client	Adopt an animal (Client > Adopt Animal)	Adopt an animal!	Requires Client::adopted vector and Client::adopt method; 1 dialog
LADOPT	9	3		8			Staff	List adopted animals (Client > List Adopted and Animal > List Adopted)	See which client adopted which animal	Requires Client::num_adopted and animal methods; 1 dialog to select the client; Mainwin::on_list_adopted_click
SAVE	10	4		13			Manager	Save the data to a default file (File > Save)	Persist our data through the years	Requires Animal::save, Dog::save, Cat::save, and Rabbit::save; Shelter::save; Shelter::filename with getter and setter; and Mainwin::on_save_click
LOAD	11	4		5			Manager	Load the data from a default file (File > Open)	Persist our data through the years	Requires Animal::Animal(ist), Dog::Dog, Cat::Cat, and Rabbit::Rabbit; Shelter::Shelter; and Mainwin::on_open_click; dialog and logic for handling “dirty” data (baseline and adapt from Paint(17) if you don’t have it already)
NEW	12	5		5			Director	Create a new shelter (File > New)	Open additional shelters as needed	Requires Mainwin::on_new_shelter_click;
SAVEF	13	5		5			Director	Save the data to a specified file (File > Save As)	Backup or baseline a new shelter	Requires Mainwin::on_save_as_click; Shelter::set_filename; adding Gtk::FileChooserDialog (baseline from Paint(17) if you don’t have it already); set filename in Shelter
LOADF	14	5		5			Director	Load the data from a specified file (File > Open)	Work with multiple shelters	If the current data is unsaved, display a custom dialog asking whether to save it, discard it, or cancel, and respond accordingly. Requires adding Gtk::FileChooserDialog (baseline from Paint(17) if you don’t have it already).
ABOUT	15	5		2			Director	Display version and required attributions (Help > About)	Stay legal and in control	Requires adding Mainwin::on_about_click with Gtk::AboutDialog. Include a properly licensed logo!
PHOTO	16		32	8			Client	See photo and information about an available animal (Animal > View)	Decide if it’s right for my family	Requires existing animal selection dialog + 1 dialog derived from Animal > New with a Gtk::Image, Mainwin::on_view_animal_click.
NANIM	17		20	5			Client	Create new animals and / or clients during adoption	Simplify the adoption process	Add “New Client” button to the client selection dialog; Add “New Animal” button to the animal selection dialog; add logic to integrate smoothly
ROLE	18		52	13			Director	Select role with authentication and selected sensitivity (Role > Client, Staff, Manager, and Director)	Limit features to appropriate users	Add _role attribute to Shelter. Add “Select Role” dialog (Client, Staff, Manager, and Director) with preset password validation (except Client), set sensitivity of menu items and buttons per User_Interface_Full.pdf
PROP	19		20	5			Manager	Display Shelter properties (File > Properties...)	Monitor Shelter operation	In a custom dialog, display the name of the shelter, number of clients, number of available animals of each type, and number of adopted animals
UNDO	20		32	8			Staff	Undo a change to the Shelter records (Edit > Undo)	Correct errors	Stack of Undo objects should track ONLY new animal (remove the animal from available), new client (remove the client from the list of clients), and adoptions (move animal from client back to available), Requires Undo object with pointer to one animal and one client; implementation is obvious.
RANIM	21		12	3			Staff	See all animals the shelter has encountered (Report > Animals)	Estimate the shelter’s impact	No additional dialogs required, but must iterate through all clients to assemble addopted animals with those on available vector
RCLIENT	22		8	2			Staff	See all clients and the animals they have adopted in a single report (Report > Clients)	Quickly find an adopted animal	No additional dialogs required, but must iterate through all clients to assemble data including adopted animals. Very similar to Report > Animals.
STAFF	23		84	21			Director	Maintain explicit lists of staff, managers, and directors (Edit > Staff, Manager, and Director)	Manage shelter operation	Derive a Staff class from Client, adding enum class Role (staff, manager, director), salary, and password. Create edit dialog to modify this data, selecting from list, with a New button to create new staff member. Modify Role > (role) password to validate against named staff’s unique password.
ACTIVE	24		32	8			Manager	Set clients, staff, directors, and managers “inactive”, and restore to “active”	Retain staffing info even when staff is on leave or quits	Add an _active bool, default true, to Staff class, and add to the edit dialog. Filter out inactive staff members from all ComboBoxText and similar selections EXCEPT the edit dialog (so they can be reactivated). Don’t allow inactive staff to log in.
Product Backlog Burn Chart
Sprints
Features Remaining at end of Sprint

## Sprint 01 Backlog
Sprint #	1		Complete Fields in Green!!!
Start on	Oct 29		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 05
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	1
Day 1 Left	1	0
Day 2 Left	1	0
Day 3 Left	1	0
Day 4 Left	1	0
Day 5 Left	1	0
Day 6 Left	1	0
Day 7 Left	1	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1			--> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
Sprint Burn Chart
Days
Tasks

## Sprint 02 Backlog
Sprint #	2		Complete Fields in Green!!!
Start on	Nov 05		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 12
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	1
Day 1 Left	1	0
Day 2 Left	1	0
Day 3 Left	1	0
Day 4 Left	1	0
Day 5 Left	1	0
Day 6 Left	1	0
Day 7 Left	1	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1			--> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
Sprint Burn Chart
Days
Tasks

## Sprint 03 Backlog
Sprint #	3		Complete Fields in Green!!!
Start on	Nov 12		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 19
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	1
Day 1 Left	1	0
Day 2 Left	1	0
Day 3 Left	1	0
Day 4 Left	1	0
Day 5 Left	1	0
Day 6 Left	1	0
Day 7 Left	1	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1			--> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
Sprint Burn Chart
Days
Tasks

## Sprint 04 Backlog
Sprint #	4		Complete Fields in Green!!!
Start on	Nov 19		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 26
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	1
Day 1 Left	1	0
Day 2 Left	1	0
Day 3 Left	1	0
Day 4 Left	1	0
Day 5 Left	1	0
Day 6 Left	1	0
Day 7 Left	1	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1			--> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
Sprint Burn Chart
Days
Tasks

## Sprint 05 Backlog
Sprint #	5		Complete Fields in Green!!!
Start on	Nov 26		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Dec 03
Demo on	Dec 05

	Remaining	Completed (this day)
Total Tasks	6
Day 1 Left	6	0
Day 2 Left	6	0
Day 3 Left	6	0
Day 4 Left	6	0
Day 5 Left	6	0
Day 6 Left	6	0
Day 7 Left	0	6

Task ID	Feature ID	Assigned To	Description	Status	Notes
1	NEW		Requires Mainwin::on_new_shelter_click;	Completed Day 7
2	SAVEF		Requires Mainwin::on_save_as_click; Shelter::set_filename; adding Gtk::FileChooserDialog (baseline from Paint(17) if you don’t have it already); set filename in Shelter	Completed Day 7
3	LOADF		If the current data is unsaved, display a custom dialog asking whether to save it, discard it, or cancel, and respond accordingly. Requires adding Gtk::FileChooserDialog (baseline from Paint(17) if you don’t have it already).	Completed Day 7
4	ABOUT		Requires adding Mainwin::on_about_click with Gtk::AboutDialog. Include a properly licensed logo!	Completed Day 7
5	PHOTO		Requires existing animal selection dialog + 1 dialog derived from Animal > New with a Gtk::Image, Mainwin::on_view_animal_click.	Completed Day 7
6	NANIM		Add “New Client” button to the client selection dialog; Add “New Animal” button to the animal selection dialog; add logic to integrate smoothly	Completed Day 7
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
Sprint Burn Chart
Days
Tasks