Please enter your name as it appears in Blackboard.
Please enter 2 or 3 capital letters that will represent you in the "Assigned To" column on each Sprint Backlog tab of this spreadsheet.
Please enter your UTA student ID number.
This cell may only contain a valid sprint number - an integer between 1 and the number of sprints in the project. Or it may be left blank (hint: use the Delete key).
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
## Product_Backlog
Product Name:	C1325 Mav’s Ultimate Sweet Shop (MUSS)					Complete Fields in Green!!!
Team ID:

Name:	Benjamin Lemke
Initials:	BL
Student ID:	1001645728

Teaming is not available for this assignment!
Optional teaming may be available in future assignments

	Remaining	Completed (this sprint)
Total Features	23		Total
Sprint 1 Left	17	6	1
Sprint 2 Left	17	0	2		Note: You are NOT penalized for not reaching 0 features remaining! Some of these are bonus features.

				Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
				Additional features or alternate priorities may be proposed by the student but must be approved by the Product Owner in writing
			Sprints
Feature ID	Priority		Planned	Status	As a...	I want to...	So that...	Notes
				SPRINT 1 / Homework 5 starts here – due OCTOBER 15
Mainwin	1		1	Finished in Sprint 1	Sales Clerk	Add a main window with text data area	can use the application with a mouse	The text data area is a Gtk::Label on which you can later display lists of sweets or orders
FileQuit	2		1	Finished in Sprint 1	Sales Clerk	Add a menu bar with File > Quit	can exit from the window
FileNew	3		1	Finished in Sprint 1	Sales Clerk	Add File > New Store	can instance a new store without exiting
SweetsAdd	4		1	Finished in Sprint 1	Sales Clerk	Add Sweets > Add	can create new products from dialogs	For this feature you may use 2 dialogs, for name and price
SweetsList	5		1	Finished in Sprint 1	Sales Clerk	Add Sweets > List	can see a menu of our products and their prices	Put the output in the text data area (i.e., the Gtk::Label below the menu)
HelpAbout	6		1	Finished in Sprint 1	Sales Clerk	Add a Help > About menu	know who created the program and its resources
Sensitivity1	7		1		Sales Clerk	Manage menu sensitivity	avoid making errors	Sweets > List should be greyed out if no Sweets have been defined yet
FileNewBtn	8		1		Sales Clerk	Add a tool bar with a New Store button	operate MUSS with buttons	This does exactly the same thing as File > New; the stock icon is fine
FileQuitBtn	8		1		Sales Clerk	Add an Exit button aligned to the right	operate MUSS with buttons	This does exactly the same thing as File > Quit; the stock icon is fine
SweetsAddBtn	8		1		Sales Clerk	Add a New Sweet button	operate MUSS with buttons	This does exactly the same thing as Sweet > Add; credit your icon in Help > About
SweetsListBtn	8		1		Sales Clerk	Add a List Sweets button	operate MUSS with buttons	This does exactly the same thing as Sweet > List; credit your icon in Help > About
	9				Sales Clerk	Add rich text (Pango) to the about dialog	The about text is easier to understand
SweetsAddDlg	10		1		Sales Clerk	Use a single dialog for Sweets > Add	deal with fewer dialogs	The dialog should have Name and Price fields, and Create and Cancel buttons
StatusBar	10		1		Sales Clerk	Add a status bar below the text data area	obtain better feedback on program operation	This is just a window-wide Gtk::Label with messages “Added [sweetname]”, “New sweet canceled”, “Order [n] placed”, “Order canceled”, “New shop created”
				SPRINT 2 / Homework 6 starts here – due OCTOBER 22
OrdersPlace	11		2	In Work	Sales Clerk	Add Orders > Place	create orders with the mouse	You may use a sequence of dialogs, each selecting quantity and sweet, to build up the order
OrdersList	12		2	In Work	Sales Clerk	Add Orders > List	view existing orders	Ask the user for an order number, then display the order in the text data area
Sensitivity2	13		2		Sales Clerk	Manage menu sensitivity	avoid making errors	Orders > Place should be greyed out if no sweets have been defined, and Orders > List if no orders have been defined (remember to handle File > New Store!)
OrdersPlaceBtn	14		2		Sales Clerk	Add a Place an Order button	operate MUSS with buttons	This does exactly the same thing as Orders > Place; credit your icon in Help > About
OrdersListBtn	14		2		Sales Clerk	Add a List Orders button	operate MUSS with buttons	This does exactly the same thing as Orders > List; credit your icon in Help > About
Pango	15		2		Sales Clerk	Replace custom About with a Gtk::About Dialog	The about text is even easier to understand
OrdersPlaceDlg	16		2		Sales Clerk	Use a single dialog for Orders > Place	deal with fewer dialogs	The dialog must show sweets and quantities already added, allow selection of sweet from a drop-down and quantity via text or drop-down, with Add, Finish, and Cancel buttons
Save	17		2		Sales Clerk	File > Save the data to a .muss file	maintain data when the program exits	You may use a single predefined filename or the FileChooserDialog, and may define any file format you like
Load	17		2		Sales Clerk	File > Load data from a .muss file	maintain data when the program exits	Consider how to handle existing unsaved data when File > Open is requested
Product Backlog Burn Chart
Features Remaining at Start of Sprint
Sprints

## Sprint_01_Backlog
Sprint #	1		Complete Fields in Green!!!
Start on	Oct 03		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Oct 15
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	26
Day 1 Left	26	0
Day 2 Left	26	0
Day 3 Left	26	0
Day 4 Left	26	0
Day 5 Left	26	0
Day 6 Left	26	0
Day 7 Left	26	0

	Feature ID		Description	Status	Notes
	Mainwin		Add code to main-gui.cpp to create and run window instance		See e.g., the nim in-class example to help with these
	Mainwin		Add a private Gtk::Label to mainwin.h and Mainwin constructor for the text data area
	FileQuit		In Mainwin constructor, add VBox and MenuBar with File>Quit
	FileQuit		Add and implement protected on_quit_click() method		The close() method is usually best
	FileNew		Add and implement protected on_new_store_click() method and File>New
	SweetsAdd		Add a Sweets menu and an Add item
	SweetsAdd		Implement utility to read line of text via a simple dialog		OR create a custom dialog to read name and price in one step
	SweetsAdd		Add and implement protected on_add_sweet_click() method		Get the name and price to instance a Sweet to pass to _store
	SweetsList		Add and implement protected on_list_sweets_click() method and Sweets>List
	HelpAbout		Add a Help menu and an About item
	HelpAbout		Add and implement protected on_help_click() to create a MessageDialog with app and your name, license, and credits		Or skip right to the Gtk::AboutDialog class
	Sensitivity1		At end of constructor, set_sensitivity false for list sweets menu item
	Sensitivity1		At end of successful SweetsAdd, set_sensitivity true “ “ “
	FileNewBtn		In constructor, add a Gtk::Toolbar just under the MenuBar
	FileNewBtn		Configure Stock::NEW button connected to on_new_store_click()
	FileQuitBtn		Configure Stock::QUIT button connected to on_quit_click()
	SweetsAddBtn		Select appropriate Sweets icons scaled to 32x32 to 64x64ish size
	SweetsAddBtn		Configure custom button connected to on_add_sweet_click()
	SweetsListBtn		Configure custom button connected to on_list_sweets_click()
	SweetsAddDlg		Create a Gtk::Dialog
	SweetsAddDlg		Add an HBox containing a Gtk::Label and a Gtk::Entry for name
	SweetsAddDlg		Add an HBox containing a Gtk::Label and a Gtk::Entry for price
	SweetsAddDlg		Add buttons, show, and exit if Cancel was clicked
	SweetsAddDlg		Convert price text to a double, instance a Sweet, and add to _store
	StatusBar		Add a Gtk::label with HExpand just after the text data area
	StatusBar		Add set_text() method calls on the status bar where messages are needed
Sprint Burn Chart
Tasks
Days

## Sprint_02_Backlog
Sprint #	2		Complete Fields in Green!!!
Start on	Oct 15		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Oct 22
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	0
Day 1 Left	0	0
Day 2 Left	0	0
Day 3 Left	0	0
Day 4 Left	0	0
Day 5 Left	0	0
Day 6 Left	0	0
Day 7 Left	0	0

	Feature ID		Description	Status	Notes
					Create your own task (“to do”) list to the left
Sprint Burn Chart
Tasks
Days